## Sheet1
# | Task Category | Specific Requirement | Status | Notes
1 | Server Setup | Launch Debian 12 Server on AWS | ✅ Done | Server is active and accessible.
2 | Components | Install PHP 8.3 | ✅ Done | Installed.
|  | Install MySQL 8 | ✅ Done | Installed manually (Bundle method).
|  | Install Elasticsearch | ✅ Done | Installed and running on port 9200.
|  | Install Redis | ✅ Done | Installed and service is active.
3 | Magento Install | Install via Composer | ✅ Done | Project created in /var/www/html/magento.
|  | Include Sample Data | ✅ Done | sampledata:deploy run successfully.
|  | Run Setup Script | ⏳ Pending | Current Step. Fails until MySQL/Redis are linked.
|  | Set Base Domain | ⏳ Pending | Needs Nginx config finalization.
4 | Redis Config | Configure for Cache | ⏳ Pending | Will be done by the Setup Script below.
|  | Configure for Session | ⏳ Pending | Will be done by the Setup Script below.
5 | Permissions | User: test-ssh, Group: clp | ✅ Done | User created.
|  | File Ownership | ✅ Done | Permissions set on /var/www/html/magento.
|  | PHP-FPM Pool (test-ssh) | ✅ Done | Pool config created earlier.
|  | Nginx User Config | ⚠️ Partial | Need to verify nginx.conf runs as test-ssh.
6 | PHPMyAdmin | Install & Configure (pma.mgt.com) | ❌ Not Started | To be done after Magento is running.
7 | HTTPS | Redirect HTTP to HTTPS | ❌ Not Started | Nginx config step.
|  | Self-Signed SSL | ❌ Not Started | OpenSSL command needed.
8 | Varnish | Install Varnish | ❌ Not Started | To be done last.
|  | Configure Full Page Cache | ❌ Not Started | Link Magento to Varnish.